Consultation Plan for Education SPD

Timetable

- Consultation periods (4 weeks); 3-31 March 2026

- Adopt at Exec Board 12 May 2026

| Task | Task details | Task Notes | Assigned | Complete |
| --- | --- | --- | --- | --- |
| Consultation documents | General letters Open Space letter |  | SR | Emailed out in 2 batched from LDF mailbox 6/2/26 |
|  | Microsoft Forms for SPD |  | SR | Form online and open |
|  | Covering email to developers |  | SR | Emailed out SR 6/2/26 |
|  | Explanatory note for public at all deposit points | KP combined as single note for all deposit points, inc instruction for staff | KP |  |
| Planning Committee | Item is on the (Date here) Committee agenda (Jane/Phil Wye) and report (attach hyperlink when completed) has been uploaded to RMS with appendices. |  |  |  |
| Inovem consultation database email list | - List | MT provided list (check re postal preferences |  | Added to xls |
| Letters to post | Check if any postal preferences stated on lists above from Inovem and create and send letters. |  |  | MT sorted postals only from inovem (3 letters oin total as per xls |
| E-mail lists | Developers - Contacts from Uniform (Matt Anderson) applicants/agents for all major apps received from the last 2 years. - Paul T previously had 2 lists, SHLAA and call for sites. – required (need latest extraction?) Master xls sheet of email consultees | MA provided xls Paul provided xls |  | Email address provided by PaulT and Matt A added to xls along with inovem extract |
|  | Open space specific email contacts here | Save to folder |  |  |
|  | Send email to all Cllrs (from Karen Shaw or Matt ? ) | In the NCC address book, press ‘to…’ on the email, type ‘All City Cllrs’, and a group email will appear. | MJG | MJG sent 6/02/26 |
|  | Deposit points (Loxley and all libraries?) | Owing to nature of limited technical update to SPD it is not considered appropriate to despatch to all libraries. |  | SR left doc and covering note at Loxley reception and new central Library 6/2/26 |
|  | Statutory Consultation database consultees list. Form Inovem list includes Statutory consultees |  |  |  |
|  | Draft email to internal consultees | . |  | Internals provided by kate added to general list SR |
| Web site | Draft text used for web site - Open space SPD text Including latest news page | ALL |  | SR liaised with web team added 5/6/26 (including on latest news) |
|  | Web addresses here – friendly URLs - open space web site friendly URL |  |  | Sorted SR |
| Email auto response | ? |  |  |  |
| Engage Nottingham | Engage Nottingham form | Send to Aaron Simpkin | KP | KP dealing with it |
| Press release | Are we doing a Press Release? | Not required |  | Not required |
| Responses | Recording responses |  |  |  |
| Reminder email | Two weeks before end of consultation? |  |  |  |