Quality and Commissioning – Strategic Commissioning Team

CARER RESPITE SERVICES STRATEGIC COMMISSIONING REVIEW

- Aim

- A review is currently taking place of carers' respite provision. This follows on from the commissioning of carer support services. This resulted in the commissioning of a Young Carer’s Service which started on 1st July 2013 and the new Carers’ Hub which started on 1st October 2013.

- The purpose of the respite review is:

- To provide more equitable access to respite provision

- To quantify current and future spend on overnight respite

- To ensure respite provision is best value

- To align more closely with health

- To inform the procurement of  home based respite provision

Scope

- The focus of the review is on overnight respite care but will include the block funded respite commissioned by Nottingham City Council.

- The review includes respite provided through; internal residential services, private residential services, Hucknall House, block contracted respite provision, home based overnight respite and ‘Shared Lives’.

- Agreement was given to decommission the current local authority block funded community respite services and to scope the development of an Emergency Respite Service and a service for those on the edge of social care.

Amended Timeline

| Respite analysis | June – Oct13 |
| --- | --- |
| Development of proposals for home based respite provision | Sept - Nov 13 |
| Sign off for new respite provision | November 13 |
| Advertise tenders for new services | December 13 |
| Development of proposals for wider respite services | Jan – Mar 14 |
| Input to new specification for residential provision | October 13 |
| New specification for Hucknall House | March 14 |
| New tendered pre-eligibility respite services in place | April 14 |